AssetIQ Senior Engineering Fix Plan Implementation Specification for All 22 QA Findings v1.0 ¦ 23 April 2026 ¦ Prepared for: AssetIQ Engineering Team

| Scope | 22 QA findings across 4 severity tiers (5 Critical, 6 High, 7 Medium, 4 Low) |
| --- | --- |
| Phases | 4 phases spanning ~10 weeks of focused engineering work |
| Audience | Backend engineers, frontend engineers, DevOps, QA |
| Companion Doc | QA Engineering Review v1.0 (QA_Engineering_Review_AssetIQ.docx) |
| Approach | Each finding includes: files to touch, step-by-step implementation, code examples, and acceptance criteria |

# 1. How to Use This Document

This document is the engineering counterpart to the QA Engineering Review. For every finding raised by QA, this plan provides the specific implementation steps a developer needs to resolve it. Work through findings in phase order — later phases sometimes build on infrastructure added in earlier ones.

Conventions used throughout this plan File paths are relative to the project root. Code blocks show the exact changes to make. "DoD" (Definition of Done) checklists are the acceptance criteria each fix must satisfy before it can be closed.

## Phase Overview

| Phase | Timeline | Severity | Goal |
| --- | --- | --- | --- |
| Phase 1 | Weeks 1-2 | CRITICAL | Resolve all launch blockers — no customer onboarding until done |
| Phase 2 | Weeks 3-6 | HIGH | Security, compliance hardening and integration test foundation |
| Phase 3 | Weeks 7-9 | MEDIUM | Operational resilience, API hygiene, data integrity |
| Phase 4 | Weeks 10+ | LOW | Performance, tooling, and ongoing quality gates |

# 2. Phase 1 — Critical Fixes (Weeks 1–2)

All five critical findings plus two high-priority items that are tightly coupled to launch readiness. Work these in parallel across two engineers: one owns database/testing (CR-01, CR-02), the other owns billing/payments (CR-03, CR-04, CR-05).

CR-01 Generate Real Flyway V7 Baseline Migration Severity: CRITICAL Phase: Phase 1 Effort: 0.5 day

### Files to Create / Modify

- src/main/resources/db/migration/V7__baseline.sql  — replace placeholder with real schema

- src/main/resources/application.yml  — verify spring.flyway.baseline-on-migrate=true

- .github/workflows/ci.yml  — add migration integrity test job

### Implementation Steps

Step 1:  Spin up a clean local Postgres instance using docker-compose and apply migrations V1–V6 only.

Step 2:  Let Hibernate create the remaining schema via ddl-auto=create-drop against that database (set temporarily in application-dev.yml).

Step 3:  Dump the resulting schema to SQL using pg_dump:

pg_dump --schema-only --no-owner --no-acl \ -h localhost -U assetiq assetiq_db > V7__baseline.sql

Step 4:  Review the dump. Remove any Hibernate-generated index names that contain random suffixes. Rename these to stable, human-readable names (e.g., idx_asset_organisation_id).

Step 5:  Replace the placeholder in src/main/resources/db/migration/V7__baseline.sql with the cleaned dump.

Step 6:  Switch application.yml back to spring.jpa.hibernate.ddl-auto=validate (do not use create-drop in any non-test profile again).

Step 7:  Add a CI job that spins up a fresh Postgres container, runs all Flyway migrations from scratch, then runs mvn test to confirm Hibernate validation passes:

# .github/workflows/ci.yml — add to jobs: migration-integrity: runs-on: ubuntu-latest services: postgres: image: postgres:16 env: { POSTGRES_DB: assetiq_test, POSTGRES_USER: assetiq, POSTGRES_PASSWORD: test } options: --health-cmd pg_isready steps: - uses: actions/checkout@v4 - uses: actions/setup-java@v4 with: { java-version: 21, distribution: temurin } - run: mvn flyway:migrate -Dflyway.url=jdbc:postgresql://localhost/assetiq_test - run: mvn test -Dspring.profiles.active=test

Definition of Done

- V7__baseline.sql contains a complete, valid SQL schema dump (no TODO comments)

- Running all 10 migrations against a clean Postgres 16 database produces a schema that passes Hibernate validation

- CI migration-integrity job is green on the main branch

- ddl-auto=create or ddl-auto=update is removed from all non-test Spring profiles

CR-02 Establish Automated Test Baseline for Critical Paths Severity: CRITICAL Phase: Phase 1 Effort: 4–5 days

### Files to Create

- src/test/java/com/assetiq/billing/PaystackWebhookControllerTest.java

- src/test/java/com/assetiq/billing/BillingServiceImplTest.java

- src/test/java/com/assetiq/license/LicensePlanLimitsServiceTest.java

- src/test/java/com/assetiq/asset/AssetServiceImplTest.java

- src/test/java/com/assetiq/asset/AssetStateTransitionTest.java

- src/test/java/com/assetiq/compliance/ComplianceServiceImplTest.java

- src/test/java/com/assetiq/integration/PaystackIntegrationTest.java

### Implementation Steps

Step 1:  Set up a shared test base class that bootstraps Spring context with H2 + Flyway for integration tests:

@SpringBootTest @AutoConfigureMockMvc @ActiveProfiles("test") @Transactional public abstract class BaseIntegrationTest { @Autowired protected MockMvc mvc; @Autowired protected ObjectMapper mapper; // shared helper: createOrg(), createUser(), createAsset() etc. }

Step 2:  Write PaystackWebhookControllerTest. Test happy path (valid HMAC, payment.success event sets subscription ACTIVE), invalid HMAC (expect 401), and duplicate event (expect 200 but no state change):

@Test void validPaymentWebhook_activatesSubscription() throws Exception { String payload = loadJson("paystack_payment_success.json"); String sig = hmacSha256(payload, paystackSecret); mvc.perform(post("/api/v1/billing/webhook") .header("x-paystack-signature", sig) .contentType(APPLICATION_JSON).content(payload)) .andExpect(status().isOk()); assertThat(billingRepo.findByOrgId(ORG_ID).getStatus()).isEqualTo(ACTIVE); } @Test void invalidSignature_returns401() throws Exception { mvc.perform(post("/api/v1/billing/webhook") .header("x-paystack-signature", "bad") .content("{}").contentType(APPLICATION_JSON)) .andExpect(status().isUnauthorized()); }

Step 3:  Write LicensePlanLimitsServiceTest. For each plan tier, seed data at the limit boundary and assert the next creation returns an exception or HTTP 402:

@ParameterizedTest @EnumSource(PlanTier.class) void assetLimit_enforcedAtBoundary(PlanTier tier) { seedAssets(tier.getMaxAssets(), orgId); // fill to limit assertThrows(PlanLimitExceededException.class, () -> assetService.create(newAssetDto(), orgId)); }

Step 4:  Write AssetStateTransitionTest to cover all invalid transitions (e.g., IN_REPAIR -> DISPOSED must go via IN_SERVICE first):

@Test void illegalStateTransition_throwsException() { Asset a = createAsset(AssetStatus.IN_REPAIR); assertThrows(IllegalStateTransitionException.class, () -> assetService.dispose(a.getId(), orgId)); }

Step 5:  Raise the Jacoco gate in pom.xml from 30% to 40% line coverage and 25% branch coverage after the new tests are merged:

<limit> <counter>LINE</counter> <value>COVEREDRATIO</value> <minimum>0.40</minimum> <!-- raised from 0.30 --> </limit>

Definition of Done

- PaystackWebhookControllerTest covers: valid payment, invalid HMAC, duplicate event, subscription renewal, charge failure

- LicensePlanLimitsServiceTest covers all 4 limit types (assets, users, departments, locations) across all plan tiers

- AssetStateTransitionTest covers all invalid transitions (at least 8 negative test cases)

- ComplianceServiceImplTest covers BOG control evaluation logic

- CI Jacoco gate raised to 40% line coverage and remains green

- mvn verify passes on main branch with all new tests

CR-03 Standardise All Currency References to GHS Severity: CRITICAL Phase: Phase 1 Effort: 1 day

### Files to Modify

- assetiq-customer-portal/app/checkout/route.ts  — fix NGN hardcode

- assetiq-customer-portal/components/PricingTable.tsx  — update currency display

- src/main/resources/application.yml  — verify all plan amounts are GHS

- src/main/java/com/assetiq/billing/BillingServiceImpl.java  — audit currency constant

- .github/workflows/ci.yml  — add currency lint step

### Implementation Steps

Step 1:  Find every currency reference in the codebase:

# Run from project root grep -rn "NGN\¦USD\¦currency\¦naira\¦dollar" --include="*.java" --include="*.ts" --include="*.tsx" --include="*.yml" .

Step 2:  In assetiq-customer-portal/app/checkout/route.ts, replace the Paystack initialisation currency field:

// BEFORE currency: "NGN", // AFTER currency: "GHS",

Step 3:  Update all price display strings in the portal to show GHS / GH₵ symbol:

// PricingTable.tsx — update formatPrice helper const formatPrice = (amount: number) => new Intl.NumberFormat("en-GH", { style: "currency", currency: "GHS" }).format(amount);

Step 4:  Verify application.yml billing plan amounts match Paystack GHS plan codes. Add a comment to each plan entry:

billing: plans: starter: amount: 9900 # GHS 99.00 — Paystack plan code: PLN_starter_ghs currency: GHS growth: amount: 29900 # GHS 299.00 — Paystack plan code: PLN_growth_ghs currency: GHS

Step 5:  Add a CI lint step that fails if NGN or USD appear in billing-related source files:

# .github/workflows/ci.yml - name: Currency lint run: ¦ if grep -rn "NGN\¦"USD"" assetiq-customer-portal/app/checkout \ src/main/java/com/assetiq/billing; then echo "ERROR: Non-GHS currency found in billing code" exit 1 fi

Definition of Done

- grep for NGN and USD in billing-related files returns zero results

- Paystack test checkout completes in GHS — verified in Paystack test dashboard

- PricingTable renders GH₵ symbol and GHS amounts on all plan cards

- Currency lint CI step is green

- Paystack plan codes in .env.example match GHS-denominated plans

CR-04 Implement Ghana Data Protection Act (DPA 2012) Compliance Module Severity: CRITICAL Phase: Phase 1 Effort: 3–4 days

### Files to Create

- src/main/java/com/assetiq/dpa/model/ConsentRecord.java

- src/main/java/com/assetiq/dpa/model/DsarRequest.java

- src/main/java/com/assetiq/dpa/model/DataRetentionPolicy.java

- src/main/java/com/assetiq/dpa/repository/DsarRequestRepository.java

- src/main/java/com/assetiq/dpa/service/DpaService.java + DpaServiceImpl.java

- src/main/java/com/assetiq/controllers/v1/DpaController.java

- src/main/resources/db/migration/V8__dpa_module.sql

### Files to Modify

- src/main/java/com/assetiq/models/Organisation.java  — add dpoEmail, dataResidencyRegion fields

### Implementation Steps

Step 1:  Create V8__dpa_module.sql migration:

CREATE TABLE consent_record ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), organisation_id UUID NOT NULL REFERENCES organisations(id), user_id UUID NOT NULL REFERENCES users(id), purpose VARCHAR(255) NOT NULL, consented_at TIMESTAMP NOT NULL, withdrawn_at TIMESTAMP, created_at TIMESTAMP NOT NULL DEFAULT NOW() ); CREATE TABLE dsar_request ( id UUID PRIMARY KEY DEFAULT gen_random_uuid(), organisation_id UUID NOT NULL REFERENCES organisations(id), requester_email VARCHAR(255) NOT NULL, request_type VARCHAR(50) NOT NULL, -- ACCESS, ERASURE, PORTABILITY status VARCHAR(50) NOT NULL DEFAULT 'SUBMITTED', submitted_at TIMESTAMP NOT NULL DEFAULT NOW(), acknowledged_at TIMESTAMP, fulfilled_at TIMESTAMP, notes TEXT ); ALTER TABLE organisations ADD COLUMN dpo_email VARCHAR(255); ALTER TABLE organisations ADD COLUMN data_residency_region VARCHAR(50);

Step 2:  Implement DpaController with these endpoints:

POST /api/v1/dpa/consent — record user consent for a purpose DELETE /api/v1/dpa/consent/{userId} — withdraw consent (sets withdrawn_at) POST /api/v1/dpa/dsar — submit a DSAR (access/erasure/portability) GET /api/v1/dpa/dsar/{id} — get DSAR status PUT /api/v1/dpa/dsar/{id}/status — update DSAR status (admin only) GET /api/v1/dpa/export — bulk export all org data (portability)

Step 3:  Implement DpaServiceImpl.exportOrgData() to aggregate data from all relevant repositories and return a structured JSON payload that satisfies the portability requirement.

Step 4:  Add RBAC permissions: DPA_READ, DPA_WRITE, DPA_ADMIN. Map DPA_ADMIN to the ADMIN and COMPLIANCE_OFFICER roles in RolePermissionDefaults.

Step 5:  Add DPO email and data residency region fields to Organisation and expose them in OrganisationController.

Definition of Done

- V8__dpa_module.sql applies cleanly after V7

- All 6 DPA endpoints are reachable and return correct responses in integration tests

- DSAR workflow can be walked through: SUBMITTED -> ACKNOWLEDGED -> FULFILLED

- exportOrgData() returns a valid JSON payload containing assets, users, audit events for the organisation

- DPA_ADMIN permission is required for status updates; returns 403 for lower roles

- Organisation model includes dpoEmail and dataResidencyRegion fields

CR-05 Expose Mobile Money Channels in Paystack Checkout Severity: CRITICAL Phase: Phase 1 Effort: 0.5 day

### Files to Modify

- assetiq-customer-portal/app/checkout/route.ts  — add channels param

- assetiq-customer-portal/components/PricingTable.tsx  — add MoMo UI

- assetiq-customer-portal/app/page.tsx  — update homepage payment copy

### Implementation Steps

Step 1:  In route.ts, add the channels array to the Paystack transaction initialisation payload:

// checkout/route.ts const paystackPayload = { email: customerEmail, amount: planAmount, currency: "GHS", channels: ["mobile_money", "card", "bank_transfer"], // ADD THIS metadata: { plan: planId, orgId }, };

Step 2:  Add MoMo provider badges to PricingTable beneath the "Subscribe" button:

// PricingTable.tsx <p className="text-xs text-gray-500 mt-2">Pay with</p> <div className="flex gap-2 mt-1 items-center"> <img src="/mtn-momo.svg" alt="MTN MoMo" className="h-6" /> <img src="/telecel-cash.svg" alt="Telecel Cash" className="h-6" /> <img src="/airtel-money.svg" alt="AirtelTigo Money" className="h-6" /> <img src="/visa.svg" alt="Visa" className="h-5" /> <img src="/mastercard.svg" alt="Mastercard" className="h-5" /> </div>

Step 3:  Download official MTN, Telecel, and AirtelTigo MoMo logo SVGs and add them to assetiq-customer-portal/public/.

Step 4:  Update homepage hero copy to explicitly mention Mobile Money as a payment option.

Step 5:  Test the full MoMo payment flow in the Paystack test environment using a test MoMo number.

Definition of Done

- Paystack checkout modal shows Mobile Money as a payment option (verified in test environment)

- MoMo provider logos (MTN, Telecel, AirtelTigo) are visible on all pricing cards

- A complete Mobile Money test transaction can be initiated and completed in the Paystack sandbox

- Homepage copy mentions Mobile Money by name

HI-03 Fix Standalone Edition — Resolve Missing Frontend Repository Severity: HIGH Phase: Phase 1 Effort: 1 day

### Files to Modify

- assetiq-standalone/docker-compose.standalone.yml

- assetiq-standalone/docker-compose.standalone.images.yml

- assetiq-standalone/README.md  — document repository structure

### Implementation Steps

Step 1:  Switch the standalone deployment to use pre-built Docker images for the frontend rather than building from source. Update docker-compose.standalone.images.yml:

services: frontend: image: ghcr.io/assetiq/assetiq-frontend:${ASSETIQ_VERSION:-latest} environment: - NEXT_PUBLIC_API_URL=${API_URL} restart: unless-stopped

Step 2:  Add a GitHub Actions workflow to build and push the frontend Docker image to GHCR on every release tag.

Step 3:  If source builds must be supported, add the frontend repo as a Git submodule:

git submodule add https://github.com/assetiq/assetiq-frontend.git assetiq-frontend git submodule update --init --recursive

Step 4:  Update the standalone setup wizard to detect whether the frontend image or submodule is available and fail fast with a clear error message if neither is present.

Step 5:  Add a CI smoke test that validates docker compose config on the standalone Compose file:

- name: Validate standalone compose run: docker compose -f assetiq-standalone/docker-compose.standalone.images.yml config --quiet

Definition of Done

- docker compose -f assetiq-standalone/docker-compose.standalone.images.yml up starts all 5 services without build errors

- Frontend image is published to GHCR on release tags

- CI validates standalone compose file on every PR

- README documents the exact setup steps for a self-hosted customer

HI-06 Complete EndOfLifeAlertJob Notification Dispatch Severity: HIGH Phase: Phase 1 Effort: 1 day

### Files to Modify

- src/main/java/com/assetiq/jobs/EndOfLifeAlertJob.java  — remove TODOs, implement dispatch

- src/test/java/com/assetiq/jobs/EndOfLifeAlertJobTest.java  — new test file

### Implementation Steps

Step 1:  Replace the 4 TODO comments in EndOfLifeAlertJob with real notification dispatch. Inject NotificationService and EmailService:

@Autowired private NotificationService notificationService; @Autowired private EmailService emailService; private void dispatchAlert(Asset asset) { // In-app notification to asset owner notificationService.create(NotificationDto.builder() .userId(asset.getAssignedUserId()) .type(NotificationType.ASSET_EOL_WARNING) .message("Asset '" + asset.getName() + "' is approaching end-of-life on " + asset.getEolDate()) .referenceId(asset.getId()) .build()); // Email to department manager emailService.sendAssetEolAlert(asset); }

Step 2:  Add an EmailTemplate for end-of-life alerts in src/main/resources/templates/emails/asset-eol-alert.html.

Step 3:  Write EndOfLifeAlertJobTest that seeds an asset with an EOL date 30 days in the future, runs the job, and asserts a notification record is created:

@Test void job_createsNotificationForNearEolAsset() { Asset a = createAsset(LocalDate.now().plusDays(25)); endOfLifeAlertJob.run(); List<Notification> notifs = notificationRepo.findByUserId(a.getAssignedUserId()); assertThat(notifs).hasSize(1); assertThat(notifs.get(0).getType()).isEqualTo(NotificationType.ASSET_EOL_WARNING); }

Definition of Done

- EndOfLifeAlertJob contains no TODO comments

- Running the job against seeded near-EOL assets creates in-app notification records

- Email dispatch is called (verified via MockBean or email outbox in tests)

- EndOfLifeAlertJobTest has at least 3 test cases: within window, outside window, already notified

# 3. Phase 2 — High Priority Fixes (Weeks 3–6)

These fixes build the security and compliance foundation needed for regulated enterprise customers. HI-01 and HI-02 continue the testing work from Phase 1. HI-04 and HI-05 address security and data sovereignty requirements.

HI-01 Add Integration Tests for All Paystack Webhook Handlers Severity: HIGH Phase: Phase 2 Effort: 2 days

### Files to Create

- src/test/java/com/assetiq/billing/PaystackWebhookIntegrationTest.java

- src/test/resources/fixtures/paystack_charge_success.json

- src/test/resources/fixtures/paystack_subscription_not_renew.json

- src/test/resources/fixtures/paystack_subscription_disable.json

### Implementation Steps

Step 1:  Create JSON fixture files for each Paystack event type. Use real Paystack event shapes (copy from Paystack docs):

// paystack_charge_success.json { "event": "charge.success", "data": { "reference": "TEST_REF_001", "amount": 9900, "currency": "GHS", "metadata": { "orgId": "{{ORG_ID}}", "plan": "starter" } } }

Step 2:  Create a HMAC test helper that signs payloads with the test Paystack secret:

public static String sign(String payload, String secret) throws Exception { Mac mac = Mac.getInstance("HmacSHA512"); mac.init(new SecretKeySpec(secret.getBytes(), "HmacSHA512")); return Hex.encodeHexString(mac.doFinal(payload.getBytes())); }

Step 3:  Write integration tests for each webhook event type: charge.success, subscription.not_renew, subscription.disable, invoice.payment_failed.

Step 4:  Assert not only HTTP status but also database state after each event (e.g., after subscription.disable, organisation billing_status should be SUSPENDED).

Definition of Done

- Tests cover all 4 webhook event types

- Each test asserts resulting database state, not just HTTP 200

- Negative case: tampered payload returns 401 — confirmed in test

- Replay case: sending the same event twice produces idempotent result

HI-02 Complete Plan Limit Enforcement Test Coverage Severity: HIGH Phase: Phase 2 Effort: 1 day

### Files to Create / Modify

- src/test/java/com/assetiq/license/PlanLimitEnforcementTest.java  — new parameterised tests

- src/main/java/com/assetiq/license/LicensePlanLimitsService.java  — audit all 4 limit types

### Implementation Steps

Step 1:  Audit LicensePlanLimitsService and confirm all 4 limit types (assets, users, departments, locations) are checked in the appropriate service create() methods. If any are missing, add them.

Step 2:  Write a @ParameterizedTest using @MethodSource that tests every limit type across every plan tier:

@ParameterizedTest @MethodSource("limitScenarios") void limitEnforced_atBoundary(String limitType, PlanTier tier, int limit) { seedEntities(limitType, limit, orgId); // seed to exact limit assertThrows(PlanLimitExceededException.class, () -> createEntity(limitType, orgId)); // one more should fail assertThat(countEntities(limitType, orgId)).isEqualTo(limit); // DB unchanged } static Stream<Arguments> limitScenarios() { return Stream.of( Arguments.of("assets", STARTER, 250), Arguments.of("assets", GROWTH, 1000), Arguments.of("users", STARTER, 10), Arguments.of("departments", STARTER, 5) // ... all combinations ); }

Step 3:  Add a concurrency test that fires 10 simultaneous asset creation requests when the org is 1 below the limit, and asserts exactly 1 succeeds:

@Test void concurrentCreation_doesNotExceedLimit() throws Exception { seedAssets(tier.getMaxAssets() - 1, orgId); ExecutorService pool = Executors.newVirtualThreadPerTaskExecutor(); List<Future<Boolean>> futures = IntStream.range(0, 10) .mapToObj(i -> pool.submit(() -> tryCreateAsset(orgId))) .collect(toList()); long successes = futures.stream().filter(f -> getQuietly(f)).count(); assertThat(successes).isEqualTo(1); }

Definition of Done

- All 4 limit types tested across all plan tiers (parameterised)

- Concurrency test confirms limit is not exceeded under race conditions

- Database count is verified to be unchanged after a rejected creation

HI-04 Add Webhook Replay Attack Protection Severity: HIGH Phase: Phase 2 Effort: 1 day

### Files to Modify

- src/main/java/com/assetiq/webhooks/WebhookVerificationService.java  — add timestamp + nonce check

- src/main/resources/application.yml  — add webhook.replay-window-seconds=300

### Files to Create

- src/test/java/com/assetiq/webhooks/WebhookReplayProtectionTest.java

### Implementation Steps

Step 1:  Require a Paystack-Webhook-Timestamp header on all incoming webhooks. In WebhookVerificationService:

public void verify(HttpServletRequest request, String payload) { String sig = request.getHeader("x-paystack-signature"); String tsHeader = request.getHeader("paystack-webhook-timestamp"); // 1. Timestamp check — reject if > 5 minutes old if (tsHeader != null) { long ts = Long.parseLong(tsHeader); long ageSeconds = Instant.now().getEpochSecond() - ts; if (ageSeconds > replayWindowSeconds) { throw new WebhookReplayException("Webhook timestamp too old: " + ageSeconds + "s"); } } // 2. Nonce check — reject duplicate event IDs String eventId = extractEventId(payload); if (eventId != null && redisTemplate.opsForValue().setIfAbsent( "wh:seen:" + eventId, "1", Duration.ofHours(24)) == Boolean.FALSE) { throw new WebhookReplayException("Duplicate webhook event: " + eventId); } // 3. HMAC signature check (existing) validateSignature(payload, sig); }

Step 2:  Return HTTP 200 (not 4xx) for duplicate events so Paystack does not keep retrying — just skip processing:

catch (WebhookReplayException e) { log.info("Skipping duplicate/replayed webhook: {}", e.getMessage()); return ResponseEntity.ok().build(); // acknowledge to Paystack, skip processing }

Step 3:  Write WebhookReplayProtectionTest with three cases: fresh webhook (passes), old timestamp (rejected), duplicate event ID (acknowledged but not reprocessed).

Definition of Done

- Webhook with timestamp > 5 minutes old is acknowledged but not processed

- Duplicate event ID within 24 hours is acknowledged but not reprocessed

- Fresh valid webhook still processes correctly

- Redis TTL on seen event keys is set to 24 hours

HI-05 Add Tenant-Level Data Residency Controls Severity: HIGH Phase: Phase 2 Effort: 1.5 days

### Files to Modify

- src/main/java/com/assetiq/models/Organisation.java  — add dataResidencyRegion field

- src/main/java/com/assetiq/storage/StorageService.java  — enforce residency in file operations

- src/main/resources/db/migration/V9__data_residency.sql

### Implementation Steps

Step 1:  Add dataResidencyRegion to the Organisation model and migration:

-- V9__data_residency.sql ALTER TABLE organisations ADD COLUMN data_residency_region VARCHAR(50); COMMENT ON COLUMN organisations.data_residency_region IS 'ISO region code for data storage (e.g. af-south-1 for Ghana/West Africa)';

Step 2:  In StorageServiceImpl, before accepting any file upload, validate that the configured S3 endpoint corresponds to the organisation's required region:

public void upload(MultipartFile file, UUID orgId) { Organisation org = orgRepo.findById(orgId).orElseThrow(); if (org.getDataResidencyRegion() != null) { String configuredRegion = resolveRegionFromEndpoint(org.getS3Endpoint()); if (!configuredRegion.startsWith(org.getDataResidencyRegion())) { throw new DataResidencyViolationException( "Storage endpoint region " + configuredRegion + " does not satisfy residency requirement: " + org.getDataResidencyRegion()); } } // ... proceed with upload }

Step 3:  Expose dataResidencyRegion in OrganisationController PUT endpoint. Require ADMIN permission to update it. Log the change to the audit trail.

Definition of Done

- V9__data_residency.sql applies cleanly

- Uploading a file for an org with a residency requirement and a non-matching S3 endpoint throws DataResidencyViolationException

- Residency check is skipped when dataResidencyRegion is null (backward compatible)

- PATCH /api/v1/organisations/{id} accepts and persists dataResidencyRegion with ADMIN permission

- Residency field change appears in the AuditEvent stream

# 4. Phase 3 — Medium Priority Fixes (Weeks 7–9)

Operational resilience, API hygiene, data integrity, and observability improvements. These can be worked in parallel by different team members.

ME-01 Add TTL-Based Cleanup for Idempotency Keys Severity: MEDIUM Phase: Phase 3 Effort: 0.5 day

### Files to Modify

- src/main/java/com/assetiq/models/IdempotencyRecord.java  — add processedAt timestamp

- src/main/java/com/assetiq/jobs/IdempotencyCleanupJob.java  — new scheduled job

- src/main/resources/db/migration/V10__idempotency_ttl.sql

### Implementation Steps

Step 1:  Add processedAt to IdempotencyRecord and migration:

-- V10__idempotency_ttl.sql ALTER TABLE idempotency_records ADD COLUMN processed_at TIMESTAMP NOT NULL DEFAULT NOW(); CREATE INDEX idx_idempotency_processed_at ON idempotency_records(processed_at);

Step 2:  Create a scheduled cleanup job that deletes records older than 72 hours:

@Component @Slf4j public class IdempotencyCleanupJob { @Autowired private IdempotencyRepository repo; @Scheduled(cron = "0 0 2 * * *") // 2am daily public void cleanup() { int deleted = repo.deleteByProcessedAtBefore(Instant.now().minus(72, HOURS)); log.info("Idempotency cleanup: deleted {} records", deleted); } }

Definition of Done

- V10 migration adds processed_at column with index

- IdempotencyCleanupJob deletes records older than 72 hours when run

- Job is scheduled and runs in CI environment without errors

ME-02 Add Retry Logic and Dead-Letter Handling to Async Jobs Severity: MEDIUM Phase: Phase 3 Effort: 1.5 days

### Files to Create / Modify

- src/main/java/com/assetiq/config/AsyncConfig.java  — add retry configuration

- src/main/java/com/assetiq/jobs/FailedTaskRecord.java  — new entity for DLQ

- src/main/resources/db/migration/V11__failed_tasks.sql

### Implementation Steps

Step 1:  Add Spring Retry to pom.xml and enable it:

<dependency> <groupId>org.springframework.retry</groupId> <artifactId>spring-retry</artifactId> </dependency> // AssetIQApplication.java @EnableRetry

Step 2:  Annotate critical async methods with @Retryable and @Recover:

@Async @Retryable(maxAttempts = 3, backoff = @Backoff(delay = 2000, multiplier = 2)) public void sendNotificationAsync(NotificationDto dto) { notificationService.create(dto); } @Recover public void recoverNotification(Exception e, NotificationDto dto) { log.error("Notification delivery failed after retries: {}", dto, e); failedTaskRepo.save(FailedTaskRecord.of("NOTIFICATION", dto, e.getMessage())); }

Step 3:  Create a failed_tasks table and FailedTaskRecord entity for the dead-letter queue. Add an admin endpoint to list and retry failed tasks.

Definition of Done

- Critical async methods (notification dispatch, email sending, webhook delivery) are annotated with @Retryable

- Failed tasks after 3 retries are written to failed_tasks table

- GET /api/v1/admin/failed-tasks lists unresolved failures

- POST /api/v1/admin/failed-tasks/{id}/retry re-enqueues a failed task

ME-03 Audit and Document Rate Limit Coverage on Write Endpoints Severity: MEDIUM Phase: Phase 3 Effort: 0.5 day

### Files to Modify

- src/main/java/com/assetiq/config/RateLimitingConfig.java  — add write-endpoint limits

- src/main/java/com/assetiq/controllers/v1/AssetController.java  — verify @RateLimited present on POST/PUT/DELETE

### Implementation Steps

Step 1:  Run a grep to find all POST, PUT, DELETE endpoints and check which ones have the @RateLimited annotation (or equivalent filter coverage):

grep -rn "@PostMapping\¦@PutMapping\¦@DeleteMapping\¦@PatchMapping" \ src/main/java/com/assetiq/controllers/ ¦ wc -l grep -rn "@RateLimited" src/main/java/com/assetiq/controllers/ ¦ wc -l # These two numbers should match

Step 2:  Add stricter Bucket4j limits for bulk and deletion operations (e.g., 20 req/min):

// RateLimitingConfig.java Bucket bulkImportBucket = Bucket.builder() .addLimit(Bandwidth.classic(5, Refill.greedy(5, Duration.ofMinutes(1)))) .build(); Bucket deletionBucket = Bucket.builder() .addLimit(Bandwidth.classic(20, Refill.greedy(20, Duration.ofMinutes(1)))) .build();

Step 3:  Document the rate limit matrix in a table comment in RateLimitingConfig.java and in the Swagger API description.

Definition of Done

- All POST/PUT/DELETE/PATCH endpoints are covered by rate limiting (grep count matches)

- Bulk import endpoint has a stricter limit (5 req/min)

- Rate limit tiers are documented in RateLimitingConfig.java header comment

ME-04 Enable Correlation ID Tracking by Default Severity: MEDIUM Phase: Phase 3 Effort: 0.5 day

### Files to Modify

- src/main/resources/application.yml  — set correlation-id.enabled=true

- src/main/java/com/assetiq/config/CorrelationIdFilter.java  — propagate to outbound calls

### Implementation Steps

Step 1:  Set correlation-id.enabled=true in application.yml (default, all profiles).

Step 2:  Ensure the X-Correlation-ID header is propagated to all outbound HTTP calls (email service, webhook delivery, S3 calls). Add it to the RestTemplate/WebClient interceptors:

// CorrelationIdRestTemplateInterceptor.java @Override public ClientHttpResponse intercept(HttpRequest req, byte[] body, ClientHttpRequestExecution exec) throws IOException { String correlationId = MDC.get("correlationId"); if (correlationId != null) { req.getHeaders().set("X-Correlation-ID", correlationId); } return exec.execute(req, body); }

Step 3:  Add correlationId to the Sentry scope so it appears in Sentry error reports.

Definition of Done

- correlation-id.enabled defaults to true in application.yml

- X-Correlation-ID header is present in all outbound HTTP requests

- correlationId appears in Sentry event breadcrumbs

- Log lines for a single request share the same correlationId in local dev

ME-05 Fix Lombok @Data on JPA Entities — Unsafe equals/hashCode Severity: MEDIUM Phase: Phase 3 Effort: 1 day

### Files to Modify

- src/main/java/com/assetiq/models/*.java  — all 58 entity files

### Implementation Steps

Step 1:  Run a grep to find all entities with @Data:

grep -rn "@Data" src/main/java/com/assetiq/models/

Step 2:  For each entity, replace @Data with explicit annotations. Follow the pattern already used in Asset.java:

// BEFORE (unsafe) @Data @Entity public class Department { ... } // AFTER (safe) @Getter @Setter @ToString(exclude = {"assets", "users"}) // exclude collections to avoid lazy-load @EqualsAndHashCode(onlyExplicitlyIncluded = true) @Entity public class Department { @Id @EqualsAndHashCode.Include private UUID id; // ... other fields }

Step 3:  After updating all entities, run the full test suite to confirm no regressions. Particular attention to: Set-based deduplication in service layer, equals checks in test assertions.

Definition of Done

- grep for "@Data" in models/ package returns zero results

- All entities use @EqualsAndHashCode(onlyExplicitlyIncluded = true) with @Id field included

- All collection fields excluded from @ToString to prevent lazy-load exceptions

- Full test suite passes after the change

ME-06 Document API Versioning Policy and Add Sunset Headers Severity: MEDIUM Phase: Phase 3 Effort: 0.5 day

### Files to Create / Modify

- src/main/java/com/assetiq/config/ApiVersioningConfig.java  — add Sunset header filter

- docs/API_VERSIONING_POLICY.md  — new policy document

### Implementation Steps

Step 1:  Write and commit API_VERSIONING_POLICY.md that specifies: v1 is current and supported for at least 12 months post-GA, breaking changes require a new version, 6-month deprecation notice minimum.

Step 2:  Remove the empty v2 routing namespace from ApiVersioningConfig (or keep it but document it as "reserved").

Step 3:  Add a response filter that injects Deprecation and Sunset headers on any v1 endpoints that are planned for removal:

// DeprecationHeaderFilter.java if (isDeprecatedEndpoint(request.getRequestURI())) { response.setHeader("Deprecation", "true"); response.setHeader("Sunset", "Sat, 01 Jan 2028 00:00:00 GMT"); response.setHeader("Link", "<https://docs.assetiq.com/api/v2>; rel=\"successor-version\""); }

Definition of Done

- API_VERSIONING_POLICY.md is committed and linked from the Swagger UI description

- Empty v2 namespace is either removed or documented

- Deprecated endpoints (if any) serve Sunset and Deprecation headers

ME-07 Extend Audit Trail to SSO, Storage, and Billing Config Changes Severity: MEDIUM Phase: Phase 3 Effort: 1 day

### Files to Modify

- src/main/java/com/assetiq/controllers/v1/SsoConfigController.java

- src/main/java/com/assetiq/controllers/v1/BillingController.java

- src/main/java/com/assetiq/services/impl/StorageConfigServiceImpl.java

### Implementation Steps

Step 1:  Create a reusable @AuditConfigChange aspect or annotation that controllers can use to automatically log configuration changes to the AuditEvent stream:

@Aspect @Component public class ConfigChangeAuditAspect { @Around("@annotation(AuditConfigChange)") public Object auditChange(ProceedingJoinPoint pjp, AuditConfigChange annotation) throws Throwable { Object result = pjp.proceed(); auditService.log(AuditEvent.builder() .type(annotation.value()) .actor(SecurityContextHolder.getContext().getAuthentication().getName()) .timestamp(Instant.now()) .build()); return result; } }

Step 2:  Annotate all write methods in SsoConfigController, BillingController, and StorageConfigServiceImpl with @AuditConfigChange("SSO_CONFIG_CHANGED"), @AuditConfigChange("BILLING_CONFIG_CHANGED"), etc.

Definition of Done

- Updating SSO configuration creates an AuditEvent with actor, timestamp, and change type

- Updating S3 storage config creates an AuditEvent

- Updating billing plan or Paystack key creates an AuditEvent

- These events are visible in GET /api/v1/audit/events with appropriate filtering

# 5. Phase 4 — Low Priority Fixes (Week 10+)

Quality-of-life improvements, performance hardening, and ongoing tooling. These can be picked up by any engineer as capacity allows.

LO-01 Benchmark and Optimise Container Cold Start Time Severity: LOW Phase: Phase 4 Effort: 0.5 day

### Implementation Steps

Step 1:  Measure current cold start time in a Docker environment:

docker build -t assetiq:test . time docker run --env-file .env assetiq:test # Record time from container start to "Started AssetIQApplication in Xs"

Step 2:  If startup exceeds 45 seconds, enable Spring lazy initialisation for non-critical beans:

# application.yml spring: main: lazy-initialization: true

Step 3:  Add startup time as a recorded metric in the CI smoke test. Fail CI if startup exceeds 60 seconds.

Definition of Done

- Cold start time is documented in a comment in Dockerfile

- Container starts within 60 seconds in the CI Docker smoke test

- CI smoke test fails if startup exceeds 60 seconds

LO-02 Add MapStruct Mapper Contract Tests Severity: LOW Phase: Phase 4 Effort: 1 day

### Files to Create

- src/test/java/com/assetiq/mappers/AssetMapperTest.java

- src/test/java/com/assetiq/mappers/UserMapperTest.java

- src/test/java/com/assetiq/mappers/OrganisationMapperTest.java

### Implementation Steps

Step 1:  Write round-trip mapper tests for every mapper that has a custom converter. Use the @SpringBootTest slice or Mappers.getMapper():

@Test void assetToDto_allNonNullFieldsMapped() { Asset entity = AssetTestFactory.fullAsset(); AssetDto dto = mapper.toDto(entity); assertThat(dto.getId()).isEqualTo(entity.getId()); assertThat(dto.getName()).isEqualTo(entity.getName()); assertThat(dto.getStatus()).isEqualTo(entity.getStatus().name()); // ... assert every non-excluded field } @Test void assetDto_roundTrip_preservesAllFields() { AssetDto dto = AssetTestFactory.fullDto(); Asset entity = mapper.toEntity(dto); AssetDto back = mapper.toDto(entity); assertThat(back).usingRecursiveComparison().isEqualTo(dto); }

Definition of Done

- Mapper contract tests exist for at least: AssetMapper, UserMapper, OrganisationMapper

- Each test asserts that no non-excluded field is silently dropped during mapping

- Tests run in CI and are green

LO-03 Migrate Secrets to Encrypted Environment Variables Severity: LOW Phase: Phase 4 Effort: 1 day

### Files to Create / Modify

- .env.example  — annotate each secret with security classification

- docs/DEPLOYMENT.md  — document secret management approach

- .github/workflows/ci.yml  — confirm secrets are from GitHub Secrets, not files

### Implementation Steps

Step 1:  Move all secrets (JWT_SECRET, PAYSTACK_SECRET_KEY, DB_PASSWORD, SMTP_PASSWORD) from .env files to Railway encrypted environment variables (for cloud deployments) or Docker Secrets (for standalone).

Step 2:  Update docker-compose.standalone.yml to read secrets from Docker secrets or environment variables rather than a mounted .env file:

# docker-compose.standalone.yml services: backend: environment: JWT_SECRET: ${JWT_SECRET} # injected from host environment DB_PASSWORD: ${DB_PASSWORD} # Remove: env_file: .env

Step 3:  Add a secret hygiene check to CI that fails if any secret pattern appears committed to git:

- name: Secret scan uses: gitleaks/gitleaks-action@v2

Step 4:  Document the full secrets management approach in docs/DEPLOYMENT.md with separate sections for cloud (Railway) and standalone (Docker Secrets / Vault).

Definition of Done

- No plaintext secrets in any committed file (gitleaks CI scan is green)

- docs/DEPLOYMENT.md describes how to configure secrets for cloud and standalone deployments

- Standalone docker-compose reads secrets from environment variables

LO-04 Add Comprehensive Startup Health Probe Severity: LOW Phase: Phase 4 Effort: 0.5 day

### Files to Modify

- src/main/java/com/assetiq/config/StartupSecurityValidator.java  — extend with external service checks

### Implementation Steps

Step 1:  Extend StartupSecurityValidator to check Paystack key format, Redis connectivity, and S3 bucket access at application startup:

@EventListener(ApplicationReadyEvent.class) public void validateOnStartup() { validateJwtSecret(); // existing validatePaystackKey(); // new validateRedisConnection();// new validateS3Access(); // new } private void validatePaystackKey() { String key = env.getProperty("PAYSTACK_SECRET_KEY", ""); if (!key.startsWith("sk_live_") && !key.startsWith("sk_test_")) { throw new StartupValidationException( "PAYSTACK_SECRET_KEY must start with sk_live_ or sk_test_"); } } private void validateRedisConnection() { try { redisTemplate.opsForValue().get("_startup_probe"); } catch (Exception e) { throw new StartupValidationException("Cannot connect to Redis: " + e.getMessage()); } }

Step 2:  Log a clear, actionable error message for each validation failure. Do not start the application if any critical dependency is misconfigured.

Definition of Done

- Application refuses to start if PAYSTACK_SECRET_KEY has an invalid format

- Application refuses to start if Redis is unreachable

- Application logs a clear error message identifying the misconfigured service

- Existing JWT secret entropy check is preserved

# 6. Additional Security Hardening (OWASP Gaps)

These items were raised in the Security Assessment section of the QA review and do not map to numbered findings, but should be addressed alongside the phases above.

## A. Dependabot / Renovate for Dependency Scanning

Step 1:  Add a .github/dependabot.yml file:

version: 2 updates: - package-ecosystem: maven directory: "/" schedule: { interval: weekly } open-pull-requests-limit: 5 - package-ecosystem: npm directory: "/assetiq-customer-portal" schedule: { interval: weekly }

## B. SSRF Mitigation in WebhookDeliveryService

Step 1:  Before dispatching any outbound webhook, validate that the target URL is not a private IP range:

private void validateWebhookUrl(String url) throws URISyntaxException { InetAddress addr = InetAddress.getByName(new URI(url).getHost()); if (addr.isSiteLocalAddress() ¦¦ addr.isLoopbackAddress() ¦¦ addr.isLinkLocalAddress() ¦¦ addr.isAnyLocalAddress()) { throw new InvalidWebhookUrlException("Webhook URL resolves to private address: " + url); } }

## C. Generate SBOM as CI Artefact

Step 1:  Add the CycloneDX Maven plugin to pom.xml:

<plugin> <groupId>org.cyclonedx</groupId> <artifactId>cyclonedx-maven-plugin</artifactId> <version>2.7.11</version> <executions> <execution> <phase>package</phase> <goals><goal>makeAggregateBom</goal></goals> </execution> </executions> </plugin>

Step 2:  Upload target/bom.json as a CI artefact on every main branch build.

# 7. Suggested Sprint Breakdown

Assumes a 2-engineer team (Backend Engineer A and Backend/Portal Engineer B) working 2-week sprints.

| Sprint | Timeline | Engineer A | Engineer B |
| --- | --- | --- | --- |
| Sprint 1 | Wk 1–2 | CR-01 (DB baseline) + CR-02 (test framework + billing tests) | CR-03 (currency) + CR-05 (MoMo) + HI-03 (standalone) |
| Sprint 2 | Wk 3–4 | CR-04 (DPA module) + HI-06 (EOL job) | HI-01 (webhook tests) + HI-02 (limit tests) |
| Sprint 3 | Wk 5–6 | HI-04 (replay protection) + HI-05 (residency) | OWASP: Dependabot + SSRF + SBOM |
| Sprint 4 | Wk 7–8 | ME-01 + ME-02 (idempotency + retry/DLQ) | ME-03 + ME-04 (rate limits + correlation IDs) |
| Sprint 5 | Wk 9–10 | ME-05 (Lombok) + ME-06 (API versioning) | ME-07 (config audit) + LO-01 + LO-02 |
| Sprint 6 | Wk 11+ | LO-03 (secrets) + LO-04 (startup probe) | Regression sweep + coverage ratchet to 50% |

Pull Request Policy Each finding must be resolved in its own PR with: (1) the implementation, (2) the tests, (3) the CI green, and (4) the DoD checklist verified by the reviewer. PRs that touch billing, security, or the database schema require a second reviewer sign-off.

Work these findings in phase order. Close each DoD checklist before marking a finding done. After Phase 1, AssetIQ is ready for limited beta. After Phase 2, AssetIQ is enterprise production-ready.